## Runbook
S. No. | Stage | Task | Remarks
1 | UAT Checks | Open UAT editor | Taken Care
2 |  | Form should have email ids updated as per business usage | Taken Care
3 |  | if Kafka is not integrated with form, check and ensure Event Enrichment rules should not be updated in form. | Taken Care
4 |  | Replace the service mail alias name to production. (i.e) Remove NP -SERVICE-RBEFORMS@rbos.co.uk | Taken Care
5 |  | Correct the FTL color code in summary line, if it has 8 character(#2196f3e0;;). Correct color code: #2196f3; | Taken Care
6 |  | db["runtime-form-definition-revs"].aggregate([ { $match: { uuid: "REPLACE THE FORM ID"} }, { $sort: { version: -1 } }, { $limit: 1 }, { $project: { DataSchema: "$stepDefinitions.dataSchemaReference.uuid", DataVersion: "$stepDefinitions.dataSchemaReference.version", UiSchema: "$stepDefinitions.uiSchemaReference.uuid", UIVersion: "$stepDefinitions.uiSchemaReference.version", RuleSchema: "$stepDefinitions.ruleDefinitionReference.uuid", RuleVersion: "$stepDefinitions.ruleDefinitionReference.version", TemplateRef: "$ruleTemplateDataReference.uuid", TemplateVersion: "$ruleTemplateDataReference.version" }} ]) If existing form check the version of form in prod and uat. UAT version of form shoud be higher than the prod. Please use above query to check the version. | Taken Care
7 |  | If existing form is updated then INC related to fix details should be created with issue details of forms. | Taken Care
8 |  | Download latest and tested form version from UAT, | Taken Care
9 | Change and Access | Create and schedule SCR | Taken Care
10 |  | Update Live eForm Summary Page with all new forms details. | Taken Care
11 |  | Raise SLX to get temporary access of AD Group rGWSeforms-Editor-RBAdminUser | Taken Care
12 | Documentation | Prepare Checklist for SCR | Taken Care
13 |  | Take signoff for checklist by Team Head | Taken Care
14 |  | Create a folder for SCR in Teams in 'eForms Main Channel' | Taken Care
15 |  | Upload all change related documents in SCR folder in Teams | Taken Care
16 |  | Disable Autosave | Taken Care
17 |  | Refresh Ext Email Template version | Taken Care
18 |  | Check FTL name | Taken Care
19 |  | Check Service account - SERVICE-RBEFORMS@rbos.co.uk | Taken Care
20 |  | Check all email ids | Taken Care
21 |  | check mandatory fields are looking and behaving as expected | Taken Care
22 |  | if any changes are done to the form in above steps, Click on Save/ Enable auto save | Taken Care
23 |  | Download the updated form version | Taken Care
24 |  | Publish the form in runtime | Taken Care
25 |  | Perform sanity checks | Taken Care
26 | Business Checkouts | Involve business for post deployment checkouts | Taken Care
27 | UAT | Revert the service mail alias name to non production. (i.e) Add NP- SERVICE-RBEFORMSNP@rbos.co.uk | Taken Care
28 | NFT | Once prod deployment is successful, deploy UAT version in NFT | Taken Care
29 | GIT | Once prod deployment is successful, Push Prod version in GITLab | Taken Care
30 | Change and Access | update the change and request for closure | Taken Care